## Sheet1
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
End of the world | Project unnecessary | Very low | Definitive | None | None | None
Computer crash | Data Loss | Low | Low - Medium | Developer (Joe) | Recreate lost data (if any) | Using github to store code remotely and using cloud to store documents
Total computer / drive failure | Unable to complete project | Low | Medium - High | Developer (Joe) | Continue working on seperate computer | Having second computer avaialbe and using GitHub/Cloud to make it easy to transfer data over to new machine
Pushing sensitive data to GitHub | Security breach | Low | High | Developer (Joe) | Changed breached passwords or data | Avoid pushing sensitive data
Software failure | Data Loss / Unable to work | Low | Medium - High | Developer (Joe) | Recreate lost data (if any) | Using github to store code remotely and using cloud to store documents
Platform Failure (GitHub etc) | Unable to access/backup data | Low | Medium - High | Developer (Joe) | Wait for platform to come back up / do other work | None
Computer hack / virus | Security breach | Low | Medium - High | Developer (Joe) | Remove virus / Continue work on other machine | Make sure computer is secured against viruses and hackers / follow security practices
Internet outage | Unable to access internet connected services (eg GitHub) | Medium | High | Developer (Joe) | Do non-internet reliant work or use mobile phone hotspot | None
Repetitive Strain Injury (RSI) / Deep Vein Thrombosis | Unable / Difficult to work | Medium | High | Developer (Joe) | Lower workload, change posture | Good posture, taking regular breaks, walking
Dehydration | Unable / Difficult to work | Medium | Medium | Developer (Joe) | Drink water | Drink water regularly
Physical / Mental Illness | Unable / Difficult to work | Medium | Low - High | Developer (Joe) | Lower workload, request extension, take painkillers | Wash hands, maintain physical / mental health through exercise
Application fails to function as intended | Poor grade | Low - Medium | Very High | Developer (Joe) | Fix (if time remains) | Plan ahead, follow best practices and allow time to check and test work